## Sheet1
Task	Description	Due Date
Research on the type of DB to use	Debate on whether to go with NoSQL or relational DB	09/13/23
Refine the existing ERD model	Follow up during CTP office hours	09/13/23
Refine user workflow	Refine the existing version as seen in initial design document	09/17/23
Built out the backend	Using Express, NodeJS,	09/30/23
Built out the frontend	Using React	10/15/23
Deliver minimum viable product		10/30/23
Incorporate vFC sharing	Allow site members to share sets from their library	11/15/23
Incorporate Deepl	Language translation (tentative)	11/15/23
Incorporate localization	Tentative	11/25/23
Incorporate internationalization	Tentative	11/25/23