## Sheet1
Date	Task	Duration (min)	Notes	Activity Type
Friday, August 25, 2023	Brainstorm potential project	60	Brain storm ideas for the project.	Design
Friday, August 25, 2023	Orientation	75		Other
Saturday, August 26, 2023	Brainstorm potential project	90	Continued brain storming project ideas.	Design
Saturday, August 26, 2023	MERN stack tutorial	150	Explored MERN stack, which may be used for the project.	Research/training/learning
Sunday, August 27, 2023	MERN stack tutorial	120	Continued with the tutorial, which will be used for the project	Research/training/learning
Sunday, August 27, 2023	Shortlist and finalize potential projects	90	Finalized ideas	Design
Monday, August 28, 2023	Draft responses for the proposal	90	First draft.	Design
Monday, August 28, 2023	Review the Project Proposal form	15	Reviewed and copied prompts so that drafts can be done before the submission.	Design
Tuesday, August 29, 2023	Reviewed and edited responses for the proposal	90	Discarded sections of responses.	Design
Thursday, August 31, 2023	Final review and proposal submission.	30	Final review and additional edits for the submission.	Design
Friday, September 1, 2023	MERN stack tutorial	60	-	Research/training/learning
Sunday, September 3, 2023	MERN stack tutorial	240	Continued with the tutorial. A significant amount of time was spent downloading and installing packages to setup a temporary development machine. (Issue with the primary machine.)	Research/training/learning
Monday, September 4, 2023	Researched examples of Project Proposal	90	Researched online material. Made notes to follow up with the instructors.	Research/training/learning
Monday, September 4, 2023	MERN stack tutorial	90	Spent significant time to troubleshoot the code.	Research/training/learning
Tuesday, September 5, 2023	Office hour with Professor Lapid	45	Followed up on questions regarding deliverables.	Other
Tuesday, September 5, 2023	Reorganize notes	30	Reorganized and edited notes from the office hour.	Research/training/learning
Tuesday, September 5, 2023	Wireframe – brainstorm	60	Brain storm ideas on potential wireframe on paper. Researched sites for ideas.	Design
Wednesday, September 6, 2023	Reading – Informal Guidebook	30	Went through the 4900 Informal Guidebook	Other
Wednesday, September 6, 2023	Wireframe – brainstorm	60	Continue brain storming ideas. Finalize the ideas to be transferred to the digital version.	Design
Wednesday, September 6, 2023	Researched NoSQL vs relational DB	60	Debating between MongoDB (NoSQL) or PostgreSQL. Will follow up with the supervisor.	Research/training/learning
Friday, September 8, 2023	Learn React	180	CTP session + lab assignment.	Research/training/learning
Sunday, September 10, 2023	Wireframe – draw digital version	150	Drew wireframes via KolourPaint.	Research/training/learning
Sunday, September 10, 2023	Sitemap	60	Experimented with LibreOffice Draw but settled on Google Drawings.	Design
Sunday, September 10, 2023	Create user flowchart	120	Researched online examples. Used Google Drawings.	Design
Sunday, September 10, 2023	ERD for the database	150	Tried two utilities and settled on the ERD diagram tool from MySQL Workbench. Also, unable to get FK to appear on linked tables.	Design
Monday, September 11, 2023	Created tentative schedule.	45	For the design document.	Other
Monday, September 11, 2023	Create/revised/upload Design Document	60	-	Other
Monday, September 11, 2023	Began reviewing the next deliverable.	30	Done via BB. Documented follow up questions for office hour.	Research/training/learning
Monday, September 11, 2023	Reached out to teammate to schedule a meeting.	15	-	Team discussion, emails
Tuesday, September 12, 2023	Office hour with Professor Lapid	60	Met with Professor Lapid regarding Demo-1.	Research/training/learning
Tuesday, September 12, 2023	Meeting with teammate	30	Touched base about the project	Team discussion, emails
Wednesday, September 13, 2023	Met with CTP TA regarding DB	30	Followed up about DB choice.	Other
Thursday, September 14, 2023	Create GitHub Repo and Commit	120	Spent time troubleshooting git push from client. Look over docs to generate token.	Testing & Debugging
Friday, September 15, 2023	Learn React	120	Lecture via CTP	Research/training/learning
Friday, September 15, 2023	Touch base with supervisor	15	Followed up regarding proposal. Received feedback. Followed up with questions.	Supervisor discussion, emails
Saturday, September 16, 2023	Draft material for demo-1. Rehearse for presentation.	150	Began drafting the material for the video. Timed and rehearsed the presentation.	Design
Sunday, September 17, 2023	Create README.md	30	Did a quick overview of markdown as well.	Design
Sunday, September 17, 2023	Work on PM board	60	Created and worked on PM board. Began populating with tentative tasks.	Design
Sunday, September 17, 2023	Revised Demo-1 slides and script. Rehearsed for demo.	120	Issue with video recording. Experimented with Gnome built-in recorder. Ran into roadblocks. Unable to record via Linux Zoom.	Design
Sunday, September 17, 2023	Record video	30	Done via PowerPoint. Video appears fine under G-Drive and Windows Media Player. Issue with VLC Player (Wins) during playback. (Slide transition resulted in hiccups.)	Design
Monday, September 18, 2023	Revised ERD, sitemap, README	45	- Deleted Library table. Edited relationships. Figured out the way to add foreign key. / - Revised sitemap. / - Minor README revision.	Design
Monday, September 18, 2023	Demo-1	30	Presentation and feedback.	Other
Monday, September 18, 2023	Reorganize notes from Demo-1	15	Documented the feedback. Added notes on suggestions on the password reset feature.	Other
Monday, September 18, 2023	Test Git push	15	Tested Git push because local files and dev environment were transferred to another machine.	Testing & Debugging
Tuesday, September 19, 2023	Touch base with supervisor	15	Reviewed and documented the feedback on database. Followed up regarding teammate status from CTP.	Supervisor discussion, emails
Wednesday, September 20, 2023	Learn React	60	Went over the previous CTP video lecture. Worked with the weekly assignment.	Research/training/learning
Thursday, September 21, 2023	Touch base with supervisor	0	Followed up to confirm workload, which relates to the status with tentative teammate.	Supervisor discussion, emails
Thursday, September 21, 2023	Learn React	180	Continue going over previous CTP video lecture on React. Completed React assignment.	Research/training/learning
Friday, September 22, 2023	CTP Lecture / Learn React	150	-	Research/training/learning
Friday, September 22, 2023	Touch base with supervisor	15	Followed up regarding teammate status. Team is officially 1. No change in workload at this time.	Supervisor discussion, emails
Friday, September 22, 2023	Install & troubleshoot PostGreSQL	60	Unable to login with default account and password. Attempted to reset the password without success.	Testing & Debugging
Saturday, September 23, 2023	Resolve PostGreSQL installation issue. PERN stack tutorial	120	Took ownership of the program folder to delete remaining files. Reinstalleod PostGreSQL. Began PERN stack tutorial.	Testing & Debugging
Sunday, September 24, 2023	PERN stack tutorial	60	Continued PERN stack tutorial.	Research/training/learning
Sunday, September 24, 2023	PostgreSQL SQL shell walkthrough	120	Tutorial of PostgresSQL - SQL shell, which included practice on SQL commands.	Research/training/learning
Tuesday, September 26, 2023	JSON Web Token Tutorial	150	Learned JWT and how it can be implemented.	Research/training/learning
Wednesday, September 27, 2023	JSON Web Token Tutorial	210	Continue learning about JWT. Experimented with tutorial.	Research/training/learning
Friday, September 29, 2023	PostgreSQL SQL – Recreate schema + translate into SQL script	210	Used pgAdmin 4 → ERD Tool to create refined schema. Created enum type for flashcard set view. Generated SQL script but was unable to execute without error. Attempted to troubleshoot without success.	Testing & Debugging
Saturday, September 30, 2023	Create database tables	120	Used the generated SQL script and manually created tables on individual basis. Did not realize that double quotes forces all select and insert to be double quoted. Will have to remove all tables and recreate them.	Coding
Sunday, October 1, 2023	Delete existing tables and revise SQL script	90	Deleted all existing tables and revised existing scripts. Looked up information pertaining to UUID and installed the required module, which will be used for primary keys.	Testing & Debugging
Monday, October 2, 2023	Continue SQL script revision	60	Continue revising SQL script to create tables. Also, looked up SQL queries to add foreign keys.	Testing & Debugging
Tuesday, October 3, 2023	Continue SQL script revision	60	Continued SQL revision to create tables. Succeeded in creating 2 tables but failed on the 3rd due to constraint issue: / ERROR: there is no unique constraint matching given keys for referenced table "vflashcard_set" / Unable to find a resolution.	Testing & Debugging
Tuesday, October 3, 2023	Begin working on the app’s backend	60	-	Coding
Wednesday, October 4, 2023	DB question with CTP TA.	60	Followed up on constraint issue with the 3rd table, questions on whether UUID should be used for other primary keys.	Other
Thursday, October 5, 2023	Learn React	90	Collaborated with CTP teammate on lab with focus on React.	Coding
Thursday, October 5, 2023	Continue working on app’s backend	180	Attempted to troubleshoot the signup route without success. Issue with post request with req.body, which returns nothing.	Testing & Debugging
Friday, October 6, 2023	Troubleshoot backend server	60	Figured out the issue with the failed post request. Proper header type needed to be sent with the post request (Content-Type : application/json and Content-Length).	Testing & Debugging
Monday, October 9, 2023	Database	90	Looked up information pertaining to composite primary key. Revised so existing tables will use only primary key. (Update done via pgAdmin 4). Added 3rd (vflashcard) via SQL command line.	Coding
Monday, October 9, 2023	Work on app’s backend	120	Worked on routes for signup. Researched ways to throw error in JS so that specific errors can be thrown. Looked up SQL commands to delete row data. Coded then tested POST via POSTMAN. Also spent time in SQL shell to gain exposure to SQL queries.	Coding
Tuesday, October 10, 2023	Go over project board	30	Went over items on Github Project. Reviewed and updated tasks with notes. Created new ones.	Other
Tuesday, October 10, 2023	Continue working on app’s backend	150	Researched ways to log req.body to the screen. (Requires the use of JSON.stringify). Created login route. Tested SQL commands to query multiple column data from a table.	Coding
Friday, October 13, 2023	Read blog on bcrypt	90	Went over a posting regarding bcrypt. Experimented with the sample code.	Research/training/learning
Saturday, October 14, 2023	Follow up on bcrypt	180	Went over another posting on bcrypt, which has a longer explanation than the previous. Experimented with the examples.	Research/training/learning
Sunday, October 15, 2023	Implement bcrypt on signup + login routes	150	Implemented bcrypt on signup and login routes. Attempted to clear rows from vfc_user previously used to test the signup route. Had to cascade because due to foreign key references. Also, experienced issue when attempting to use the data returned from SQL query. Took awhile to figure out a way to get the hash so that it can be compared against the password. Added the codes/examples used to learn about bcrypt. (See Notes.)	Coding
Tuesday, October 17, 2023	SQL query tutorial	120	Went over tutorial on SQL query on join, alter tables, adding columns. Experimented with query on the PostGreSQL server. Made revisions to the vflashcard_set table. Documented the queries used. Generated new ERD from the revision. Updated the naming convention for existing ERD to maintain consistency.	Research/training/learning
Wednesday, October 18, 2023	Review JSON Web Token tutorial	60	Went through a tutorial via Digital Ocean. Experimented with the code.	Research/training/learning
Thursday, October 19, 2023	Implement function to generate JsonWebToken and middleware for authentication	180	1. Created token secret and saved under .env. / 2. Created tokenGenerator.js. Error with expiresIn but did not make headway while troubleshooting: Error: invalid expiresIn option for string payload / 3. Added middleware → auth.js / 4. Revised login route.	Coding
Friday, October 20, 2023	Learn about backend / Express	90	CTP lecture	Research/training/learning
Saturday, October 21, 2023	Troubleshoot tokenGenerator.js	90	Debugged the error: Error: invalid expiresIn option for string payload. / Also, revised signup/login routes. Input email is converted to lowercase to remove issue case sensitivity and avoid duplicate email.	Testing & Debugging
Sunday, October 22, 2023	Follow up on Express documentation	180	Followed up on the guide from lecture to develop more in-depth knowledge. Experimented with the code.	Research/training/learning
Sunday, October 22, 2023	Create other routes, troubleshoot auth.js	120	Began creating other routes necessary for vfc user. Troubleshoot auth.js but did not make any progress. Shorten vflashcard_set table to vfc_set for convenience purpose.	Coding
Monday, October 23, 2023	Touch base with supervisor	15	Followed up regarding the team status, which is now 1. Also followed up with question pertaining to JSON Web Token and Git.	Supervisor discussion, emails
Monday, October 23, 2023	Touch base with supervisor	0	Followed up with questions via Slack.	Supervisor discussion, emails
Wednesday, October 25, 2023	Debug the route to verify JSON web token	180	Reviewed several tutorials. Experimented and debugged the code.	Testing & Debugging
Thursday, October 26, 2023	Work on routes under personal profile	150	Worked on routes for personal profile. (Get public/private flashcard sets, creating new flashcard set.) Had to troubleshoot SQL queries.	Coding
Thursday, October 26, 2023	Replicate database for test purpose	30	Learned the commands to replicate the vflashcard database on the server made a duplicate database for test purpose.	Research/training/learning
Sunday, October 29, 2023	Review Git Project	30	Reviewed project board. Updated tasks status and added new ones.	Other
Sunday, October 29, 2023	Continue to work on profile routes	270	Continue working on routes under user profile: / - Update vfc_set properties / - Delete a set / - Get card from a personal set / - Get card from a public set / Unable to resolve issues from all routes above during test. / Also, shorten vflashcard table to vfc for convenience.	Coding
Monday, October 30, 2023	Debug delete card set route	45	Resolved the delete card set route issue. The path missed the ‘/’ character: / Before: lib/:param / After: /lib/:param	Testing & Debugging
Monday, October 30, 2023	Debug update card set route	120	Debugged the code and completed testing. Also, added verifySetAccess.js to check the access type argument and to convert it to lower case before insert.	Testing & Debugging
Monday, October 30, 2023	Work on profile routes: / - Delete card / - Create new card / - Debug get cards from private library	75	Created and debugged routes for delete card, create new card, and also debugged get cards from private set route. The last one can be refined, but should suffice for the time being.	Coding
Monday, October 30, 2023	Review and update project board	30	Updated tasks where appropriate.	Other
Tuesday, October 31, 2023	Rename etc.sql to SQL_Query_Journal.sql	0	Gave a more descriptive and appropriate file name.	Other
Tuesday, October 31, 2023	Work on profile routes: / 1 – Get private cards / 2 – Get public cards	60	Added verification check (either user, set access type). Tested the routes. Also, added SQL query used during the test.	Coding
Friday, November 3, 2023	Touch base with supervisor	15	Followed up about project status and evaluation.	Supervisor discussion, emails
Friday, November 3, 2023	Review requirement and plan the presentation	60	Took notes from a previous email. Created a checklist. Began brainstorming the presentation.	Other
Friday, November 3, 2023	Select presentation template	60	Looked through templates from PowerPoint, LibreOffice Impress, and Google Slides. Tried various templates to see whether they have a stylistic fit with the project. Settled with Google Slides and experimented with the templates.	Other
Friday, November 3, 2023	Draft presentation	60	Wrote out all the possible pages. Will require 2-3 passes to finalize.	Other
Saturday, November 4, 2023	Draft presentation (cont’d)	120	Reorganized and edited the previous draft. Will review again later before creating the slides.	Other
Saturday, November 4, 2023	Take and edit screenshots	30	Downloaded MySQL Workbench to export old diagrams to PNG. Took and edited screenshots of several ERD, SQL Query journal, SQL Shell.	Other
Saturday, November 4, 2023	Revise sitemap	0	Done via Google docs. Exported PNG file.	Other
Saturday, November 4, 2023	Draft presentation (cont’d)	60	Continued revising the draft for the presentation.	Other
Saturday, November 4, 2023	Take and edit screenshots (cont’d)	30	Took screenshots using Postman.	Other
Saturday, November 4, 2023	Begin work on presentation	135	Began working on presentation slides (up to 7). Minor revision on the draft.	Other
Saturday, November 4, 2023	Minor revision to the route for creating new cards	0	Minor revision on userProfile.js	Testing & Debugging
Sunday, November 5, 2023	Continue work on presentation	390	Added additional screenshots. Created new slides. Made additional revision and retake screenshots as necessary.	Other
Monday, November 6, 2023	Implement route – update existing card	30	Created the route to update an individual card. Testing completed.	Coding
Tuesday, November 7, 2023	React review	120	Reading up on documentation, learning and experimenting with code.	Research/training/learning
Thursday, November 9, 2023	Touch base with supervisor	30	Followed up my previous questions. Got recommendation on resources pertaining to JSONWebToken, pointers regarding Git and exposed API key and implications that it has on a multi user repo, implications of frontend vs backend verification/validation process.	Supervisor discussion, emails
Saturday, November 11, 2023	React review	180	Reviewed concepts from MDN site	Research/training/learning
Sunday, November 12, 2023	Began work on frontend	90	Continued reviewing React and planned the components on frontend.	Research/training/learning
Sunday, November 12, 2023	Demo-2 prep	90	Preparation work for demo-2.	Other
Sunday, November 12, 2023	Debug signup route	30	Noticed an issue with the sign up route during my demo-2 run through. Spent time correcting the issue with hashing.	Testing & Debugging
Monday, November 13, 2023	Review and update project board	30	Reviewed, updated, and created new tasks (including deliverables). Checked remaining tasks and defined new timeline.	Other
Monday, November 13, 2023	Demo-2 prep	90	Continued prepping and revising the script for demo-2. Will need a few run-through to confirm the total time. Perform final review then upload.	Other
Monday, November 13, 2023	Work on Demo-2 video	150	Used Zoom. Revised the scripts further. Practiced several times before the outtakes. Completed and uploaded the video.	Other
Tuesday, November 14, 2023	Plan out frontend	60	Drew up a checklist, including high level view, individual files	Research/training/learning
Thursday, November 16, 2023	Initialize frontend	120	Initialize the react-app. Deleted unnecessary files. Began creating the skeleton/frame.	Coding
Saturday, November 18, 2023	Add boostrap to index.html	0	For responsive websites.	Coding
Tuesday, November 21, 2023	Build signup route	120	Began building signup route. Was able to pass information to the backend and create new user account.	Coding
Wednesday, November 22, 2023	Office hour with supervisor	60	Went over question regarding frontend (react-router-dom, authentication).	Supervisor discussion, emails
Wednesday, November 22, 2023	Frontend – home + login	120	Began working on Home and Login on frontend. Also, deleted redundant SQL user data.	Coding
Thursday, November 23, 2023	Read React-Router-Dom v6 doc	60	-	Research/training/learning
Friday, November 24, 2023	Research authentication implementation on frontend	120	Looked over tutorials and react-router-dom v6 doc.	Research/training/learning
Saturday, November 25, 2023	Review PM board + checklist	0	-	Other
Saturday, November 25, 2023	Research authentication implementation on frontend (cont’d)	90	Continued researching ways to implement to authentication.	Research/training/learning
Saturday, November 25, 2023	Revise high level plan. Implement skeleton code for Profile.	30	Profile.js will consists for title bar, nav pane, and body where the main functionality will be displayed.	Coding
Sunday, November 26, 2023	Research React Router Dom v6	120	Reviewed tutorial for v6.	Research/training/learning
Monday, November 27, 2023	Frontend – authentication	120	Code the helper function.	Coding
Tuesday, November 28, 2023	Frontend – authentication debugging	60	Continued debugging the helper function.	Testing & Debugging
Tuesday, November 28, 2023	Office hour with supervisor	45	Worked on frontend authentication and was able to set localstorage with the returned token. Protected route is not redirecting to the profile.	Supervisor discussion, emails
Tuesday, November 28, 2023	Frontend – Login page and private route	90	Continued working on the protected route and login. Unable to get login to redirect to the profile page after submission.	Testing & Debugging
Wednesday, November 29, 2023	Frontend – Login page, signup page, private route	120	Continued debugging the code. Able to get the login, sign up page to redirect to the profile page after setting token with the local storage.	Testing & Debugging
Wednesday, November 29, 2023	Debug signup route	30	Issue with the signup route, which took zero length string as input but has been corrected.	Testing & Debugging
Saturday, December 2, 2023	Revise design document	0	Done to reflect the team status.	Other
Saturday, December 2, 2023	Code profile page	180	Worked on profile page. Added new pages.	Coding
Saturday, December 2, 2023	Review React Router Dom v6	90	Read up on documentation	Research/training/learning
Sunday, December 3, 2023	Follow up React Router Dom v6 doc	75	Reviewed documentation.	Research/training/learning
Sunday, December 3, 2023	Frontend – Home/Landing Page route	45	Added navigation. Modified the route under App.js	Coding
Sunday, December 3, 2023	Frontend – Profile	75	Reworked Profile. Modified route under App.js. Completed Logout page.	Coding
Monday, December 4, 2023	Frontend – Debug fetch and relative path	30	Unable to use relative path with fetch. Added proxy to package.json to resolve.	Testing & Debugging
Monday, December 4, 2023	Frontend – Private library	180	Began work on private lib route. Page is throwing errors but works with page refresh.	Coding
Monday, December 4, 2023	Frontend – Public Library	30	Began work on public lib route. Similar issue with private library.	Coding
Monday, December 4, 2023	Frontend – Debug private/public libraries	75	Continued debugging without success.	Testing & Debugging
Tuesday, December 5, 2023	Office hour with supervisor	60	Worked on the issue pertaining to cardSet.map. Root cause was due to the async nature of setting local sessions. Added await to in Login and amended useAuth (useEffect is no longer used.)	Supervisor discussion, emails
Thursday, December 7, 2023	Frontend – Private card set	150	Build page to show cards from a single set.	Coding
Thursday, December 7, 2023	Office hour with supervisor	30	Received advice and recommendation to approach individual card display, including change state and toggle, also navigation.	Supervisor discussion, emails
Thursday, December 7, 2023	Frontend – Revise private & public library, private set	30	For libraries, added condition to display empty library when empty. Also for private set, added condition to display empty set or existing title.	Coding
Friday, December 8, 2023	Frontend – Private Library set – Add toggle	120	Added toggle button to allow cards to be flipped in the private card sets.	Coding
Saturday, December 9, 2023	Frontend – Public Library set	60	Added the route to view set library.	Coding
Saturday, December 9, 2023	Frontend – Debugging Libraries route	60	Resolved issue “card.map is not a function” when flashcard set does not have any cards. Changed the backend route to return the empty set instead of message. Added relevant messages for private and public routes.	Testing & Debugging